## Process Engineering
# | Phase | Object Type/ Template | Object Name | Input/ Output/Role | Guidance | Status O-Open R-Review C-Complete D-Delete | Comments | Est Comp Date | Act Comp Date | Document Name
1 | Initiation | Task | Initiate Project |  | Identifying Stakeholders
2 | Initiation |  |  | Role | Project Manager
3 | Initiation |  |  | Role | Project Sponsor
4 | Initiation |  |  | Role | Stakeholder
5 | Initiation |  |  | Input | Product or Service Description |  | Artifact
6 | Initiation |  |  | Input | Strategic Plan |  | Artifact
7 | Initiation |  |  | Input | Business Case |  | Artifact
8 | Initiation |  |  | Input | Project Selection Criteria |  | Artifact
9 | Initiation |  |  | Input | Lessons Learned |  | Artifact
10 | Initiation |  |  | Output | Project Charter |  | Artifact
11 | Initiation |  |  | Output | Project Manager Assigned |  | Outcome
12 | Initiation |  |  | Guidance | Project Charter Template

## Roles (hidden)
# | Object Type/ Template | Object Name | Assigned To | Status O-Open R-Review C-Complete D-Delete | Comments | Est Comp Date | Act Comp Date | Document Name
1 | Role | Application Owner |  | O |  |  |  | Role-ISMM-ApplicationOwner-v1.0.rtf
2 | Role | Business Owner |  | O |  |  |  | Role-ISMM-BusinessOwner-v1.0.rtf
3 | Role | Client Services Manager |  | O |  |  |  | Role-ISMM-ClientServicesManager-v1.0.rtf
4 | Role | Digital Security Council |  | O |  |  |  | Role-ISMM-DigitalSecurityCouncil-v1.0.rtf
5 | Role | DR Plan Owner |  | O |  |  |  | Role-ISMM-DRPlanOwner-v1.0.rtf
6 | Role | DR Specialist |  | O |  |  |  | Role-ISMM-DRSpecialist-v1.0.rtf
7 | Role | FIS |  | O | This may need to be a specific FIS role - Manager, Tech Lead? |  |  | Role-ISMM-FIS-v1.0.rtf
8 | Role | Identity and Access Management Specialist |  | O |  |  |  | Role-ISMM-IAMSpecialist-v1.0.rtf
9 | Role | Information Security Manager |  | O |  |  |  | Role-ISMM-InformationSecurityManager-v1.0.rtf
10 | Role | Project Manager | N/A | C | Role previously defined |  |  | N/A
11 | Role | Project Team |  | O | This was referenced during discussions and in the workflows - not sure if this should be replaced by references to specific roles for the tasks. |  |  | Role-ISMM-ProjectTeam-v1.0.rtf
12 | Role | Recovery Team |  | O | This was referenced during discussions and in the workflows - not sure if this should be replaced by references to specific roles for the tasks. |  |  | Role-ISMM-RecoveryTeam-v1.0.rtf
13 | Role | Security Analyst |  | O |  |  |  | Role-ISMM-SecurityAnalyst-v1.0.rtf
14 | Role | Security Architect |  | O |  |  |  | Role-ISMM-SecurityArchitect-v1.0.rtf
15 | Role | Technical Manager |  | O |  |  |  | Role-ISMM-TechnicalManager-v1.0.rtf
16 | Role | Vendor |  | O | May already exist, verify in OpenUP |  |  | Role-ISMM-Vendor-v1.0.rtf